## Sprint1
BUG REPORT LIST SPRINT 1
|  | Project Name | Online Clinic Booking System | Creator | Hong
|  | Project Code | OnClinic | Version | 1.0
|  | Number of bug | 3
Function | No. | Procedure | Test Data | Expected Result | Actual Result | Severity | Discover Date | Bug Discoverer
Disease prediction and clinic suggestions | TC.13 | 1. Access booking page |  | Correct results (Viêm phổi) | Unfinished function | 1 | 2021-10-04
|  | 2. Enter age | Trẻ
|  | 3. Enter sex | Nam
|  | 4. Enter weight | Hơi gầy
|  | 5. Enter heat | Sốt nhẹ
|  | 6. Enter symptom | Ho, Đau ngực, Khó thở, Sốt, Môi khô
7. Observe result
| TC.14 | 1. Access booking page |  | Correct results (Viêm phổi) | Unfinished function | 1 | 2021-10-04
|  | 2. Enter age | Trung niên
|  | 3. Enter sex | Nữ
|  | 4. Enter weight | Gầy
|  | 5. Enter heat | Sốt cao
|  | 6. Enter symptom | Ho, Đau ngực, Khó thở, Sốt, Môi khô
7. Observe result
| TC.15 | 1. Access booking page |  | Correct results (Viêm phổi) | Unfinished function | 1 | 2021-10-04
|  | 2. Enter age | Trung niên
|  | 3. Enter sex | Nam
|  | 4. Enter weight | Hơi gầy
|  | 5. Enter heat | Sốt nhẹ
|  | 6. Enter symptom | Ho, Đau ngực, Khó thở, Sốt, Môi khô
7. Observe result
Severity levels
|  |  |  | 1 | Priority Level: High - Must be fixed
|  |  |  | 2 | Priority Level: Medium - Have to be fixed
|  |  |  | 3 | Priority Level: Low - Need to be fixed

## Sprint3
BUG REPORT LIST SPRINT 3
|  | Project Name | Online Clinic Booking System | Creator | Hong
|  | Project Code | OnClinic | Version | 1.0
|  | Number of bug | 2
Function | No. | Procedure | Test Data | Expected Result | Actual Result | Severity | Date | Bug Discoverer
Change personal information | Bug01 | 1. Access profile page |  | Error Message: " Ngày sinh không hợp lệ " | Message: "Thay đổi thành công" | 2 | 2021-11-18 | Hong
2. Press "Thay đổi thông tin cá nhân"
|  | 3. Select invalid birthday | 01/01/1849
|  | 5. Enter valid email | thanhhong24102000@gmail.com
|  | 6. Enter valid address | Hòa Xuân, Cẩm Lệ, Đà Nẵng
7. Press "Lưu thay đổi"
| Bug02 | 1. Access profile page |  | Error Message: " Ngày sinh không hợp lệ " | Message: "Thay đổi thành công" | 2 | 2021-11-18 | Hong
2. Press "Thay đổi thông tin cá nhân"
|  | 3. Select invalid birthday | 2021-10-15
|  | 4. Enter valid email | thanhhong24102000@gmail.com
|  | 5. Enter valid address | Hòa Xuân, Cẩm Lệ, Đà Nẵng
6. Press "Lưu thay đổi"
Severity levels
|  |  |  | 1 | Priority Level: High - Must be fixed
|  |  |  | 2 | Priority Level: Medium - Have to be fixed
|  |  |  | 3 | Priority Level: Low - Need to be fixed

## Sprint4
BUG REPORT LIST SPRINT 4
|  | Project Name | Online Clinic Booking System | Creator | Hong
|  | Project Code | OnClinic | Version | 1.0
|  | Number of bug | 7
Function | No. | Procedure | Test Data | Expected Result | Actual Result | Severity | Discover Date | Bug Discoverer
Registration | Bug01 | 1. Open the "OnClinic" app |  | Error message: " Lỗi đăng kí tài khoản " | Message: "Đăng ký thành công" | 2 | 2021-12-08 | Xuan
2. Press "Đăng ký"
|  | 3. Enter invalid email (no exist email) | honghong@gmail.com
|  | 4. Enter valid name | Trần Nguyễn Thanh Hồng
|  | 5. Enter valid password | hong@123
|  | 6. Enter match password | hong@123
|  | 7. Select valid birthday | 2000-10-24
|  | 8. Select valid address | Hòa Xuân, Cẩm Lệ, Đà Nẵng
9. Press "Đăng ký"
| Bug02 | 1. Open the "OnClinic" app |  | Error Message: " Vui lòng nhập đúng tên " | Message: "Đăng ký thành công" | 2 | 2021-12-08 | Xuan
2. Press "Đăng ký"
|  | 3. Enter valid email | thanhhong24102000@gmail.com
|  | 4. Enter invalid name (Wrong format) | 12345
|  | 5. Enter valid password | hong@123
|  | 6. Enter match password | hong@123
|  | 7. Select valid birthday | 2000-10-24
|  | 8. Select valid address | Hòa Xuân, Cẩm Lệ, Đà Nẵng
9. Press "Đăng ký"
| Bug03 | 1. Open the "OnClinic" app |  | Error Message: " Vui lòng nhập lại ngày sinh " | Message: "Đăng ký thành công" | 2 | 2021-12-08 | Xuan
2. Press "Đăng ký"
|  | 3. Enter valid email | thanhhong24102000@gmail.com
|  | 4. Enter valid name | Trần Nguyễn Thanh Hồng
|  | 5. Enter valid password | hong@123
|  | 6. Re-enter match password | hong@123
|  | 7. Select invalid birthday (now) | 2021-09-25
|  | 8. Select valid address | Hòa Xuân, Cẩm Lệ, Đà Nẵng
9. Press "Đăng ký"
| Bug04 | 1. Open the "OnClinic" app |  | Error Message: " Vui lòng nhập lại ngày sinh " | Message: "Đăng ký thành công" | 2 | 2021-12-08 | Xuan
2. Press "Đăng ký"
|  | 3. Enter valid email | thanhhong24102000@gmail.com
|  | 4. Enter valid name | Trần Nguyễn Thanh Hồng
|  | 5. Enter valid password | hong@123
|  | 6. Re-enter match password | hong@123
|  | 7. Select invalid birthday (before 1850) | 01/01/1854
|  | 8. Select valid address | Hòa Xuân, Cẩm Lệ, Đà Nẵng
9. Press "Đăng ký"
Heartbeat Measure | Bug05 | 1. Open OnClinic app |  | Working smooth and accurately | Unfinished function | 1 | 2021-12-09
2. Login successfully
3. Press "Đo nhịp tim" icon
4. Press "Bắt đầu đo nhịp tim"
5. Put your finger cover the back camera and wait
6. Compare results
| Bug06 | 1. Open OnClinic app |  | Alert: "Bạn chưa đặt ngón tay lên camera" | Unfinished function | 1 | 2021-12-09
2. Login successfully
3. Press "Đo nhịp tim" icon
4. Press "Bắt đầu đo nhịp tim"
5. Wait
Online Payment | Bug07 | Access online payment function |  |  | Unfinished function | 1 | 2021-12-09
Severity levels
|  |  |  | 1 | Priority Level: High - Must be fixed
|  |  |  | 2 | Priority Level: Medium - Have to be fixed
|  |  |  | 3 | Priority Level: Low - Need to be fixed