## Estimated
SPRINT 1 SPRINT BACKLOG - PLAN
Team Availability
| Name | Available Hours | Total
| Truong Gia Huy | 98 | 371 | [9 empty] | On Time
| Ngo Van Kha | 95 | [10 empty] | Lately
| Le Van Xuan | 95 | [10 empty] | Early
| Tran Nguyen Thanh Hong | 83 | [10 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10
1 | Initial Sprint 1 | Sprint Planning Meeting | All member | 8 | 0
|  | Create Sprint Backlog for Sprint 1 | Hong | 5 | 5 | 0
|  | Create Test Case Document for Sprint 1 | Huy, Hong | 6 | 6 | 3 | 0
| Design | Design UI | All member | 16 | 16 | 8 | 0
|  | Create Database | All member | 20 | 20 | 12 | 4 | 0
| Implementation | Set up front-end develop environment | All member | 20 | 20 | 16 | 16 | 12 | 0
|  | Set up back-end develop environment | All member | 20 | 20 | 20 | 20 | 20 | 20 | 0
|  | XML & JAVA - Tạo suất khám | Huy | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 0
|  | XML - Danh sách suất khám đã tạo | Kha | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 0
|  | XML & JAVA - Trang chủ phòng khám | Xuan | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 0
|  | XML & JAVA - Thông tin phòng khám | Hong | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 10 | 5 | 0
|  | XML & JAVA - Trang chủ bệnh nhân | Huy | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
|  | XML & JAVA - Đặt phòng | Kha | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
|  | XML & JAVA - Xác nhận Đặt phòng | Xuan | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
|  | Thuật toán nhập triệu chứng và tìm bệnh | All member | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 40 | 20 | 0
| Testing | Test Sprint 1 | All member | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 0
| Fix Bugs | Fix bug for Sprint 1 | All member | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 40 | 20 | 0
| Release Sprint 1 | Review Meeting | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | RetroSpective | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | Total | 379 | 371 | 343 | 324 | 316 | 304 | 284 | 264 | 244 | 224 | 209 | 194 | 179 | 144 | 124 | 104 | 84 | 64 | 44 | 24 | 4 | 0
Note on D11: ====== ID#AAAATEXZefo Ngô Văn Kha (2021-10-11 00:17:13) sao ngày 20/9 hoàn thành đc 60 điểm ------ ID#AAAATEXZefs Hồng Trần Nguyễn Thanh (2021-10-11 03:05:54) thì cái phần ni ai cũng làm đại mà kiểu như ngày 20 là hoàn thành xong vậy thôi
Note on D19: ====== ID#AAAATEXZefw Ngô Văn Kha (2021-10-11 00:33:56) mấy chỗ 20 ni răng lại làm 1 ngày duy nhất là xong đc. Phải trừ dần dần ở những ngày phía trước rồi nó mới về 0 chứ ------ ID#AAAATEXZef0 Hồng Trần Nguyễn Thanh (2021-10-11 03:00:08) thì all member mà mi mỗi đứa làm 5 tiếng thì 4 đứa 20 tiếng đúng rồi

## Actual
SPRINT 1 SPRINT BACKLOG - ACTUAL
Team Availability
| Name | Available Hours | Total
| Truong Gia Huy | 82.5 | 318 | [11 empty] | On Time
| Ngo Van Kha | 82.5 | [12 empty] | Lately
| Le Van Xuan | 82.5 | [12 empty] | Early
| Tran Nguyen Thanh Hong | 70.5 | [12 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | Actual | 2021-09-20 | 2021-09-21 | 2021-09-22 | 2021-09-23 | 2021-09-24 | 2021-09-25 | 2021-09-26 | 2021-09-27 | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10
1 | Initial Sprint 1 | Sprint Planning Meeting | All member | 8 | 8 | 0
|  | Create Sprint Backlog for Sprint 1 | Hong | 5 | 7 | 5 | 0
2
|  | Create Test Case Document for Sprint 1 | Huy, Hong | 6 | 6 | 6 | 3 | 0
| Design | Design UI | All member | 16 | 12 | 16 | 8 | 0
-4
|  | Create Database | All member | 20 | 20 | 20 | 12 | 4 | 0
| Implementation | Set up front-end develop environment | All member | 20 | 12 | 20 | 16 | 16 | 12 | 0
-8
|  | Set up back-end develop environment | All member | 20 | 18 | 20 | 20 | 20 | 12 | 0
-2
|  | XML & JAVA - Tạo suất khám | Kha | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 10 | 6 | 2 | 0
|  | XML - Danh sách suất khám đã tạo | Huy | 15 | 17 | 15 | 15 | 15 | 15 | 15 | 11 | 6 | 3 | 0
2
|  | XML & JAVA - Trang chủ phòng khám | Xuan | 15 | 16 | 15 | 15 | 15 | 15 | 13 | 10 | 5 | 2 | 0
1
|  | XML & JAVA - Thông tin phòng khám | Hong | 15 | 16 | 15 | 15 | 15 | 15 | 15 | 10 | 7 | 4 | 0
1
|  | XML & JAVA - Trang chủ bệnh nhân | Huy | 20 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 11 | 6 | 0
-2
|  | XML & JAVA - Đặt phòng | Kha | 20 | 23 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 11 | 6 | 0
3
|  | XML & JAVA - Xác nhận Đặt phòng | Xuan | 20 | 22 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 15 | 10 | 5 | 0
2
|  | Thuật toán nhập triệu chứng và tìm bệnh | All member | 60 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60
| Testing | Test Sprint 1 | All member | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 0
| Fix Bugs | Fix bug for Sprint 1 | All member | 60 | 68 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 40 | 20 | 0
8
| Release Sprint 1 | Review Meeting | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  | RetroSpective | All member | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | Total | 379 | 322 | 371 | 345 | 320 | 308 | 271 | 265 | 248 | 235 | 228 | 209 | 196 | 181 | 167 | 164 | 164 | 144 | 124 | 104 | 84 | 72 | 60

## Burn-down-Sprint 1
Estimated | Actual | Date
371 | 371 | 2021-09-20
343 | 345 | 2021-09-21
324 | 320 | 2021-09-22
316 | 308 | 2021-09-23
304 | 271 | 2021-09-24
284 | 265 | 2021-09-25
264 | 248 | 2021-09-26
244 | 235 | 2021-09-27
224 | 228 | 2021-09-28
209 | 209 | 2021-09-29
194 | 196 | 2021-09-30
179 | 181 | 2021-10-01
144 | 167 | 2021-10-02
124 | 164 | 2021-10-03
104 | 164 | 2021-10-04
84 | 144 | 2021-10-05
64 | 124 | 2021-10-06
44 | 104 | 2021-10-07
24 | 84 | 2021-10-08
4 | 72 | 2021-10-09
0 | 60 | 2021-10-10